## Sheet1
Date | Project | Task Detail | Time
2017-06-06 | List App | R&D for Upload Csv file in a bulk of data in CI | 3:00
2017-06-06 | List App | Delete Product | 1:00
2017-06-06 | List App | Export Csv File in CI | 2:00
2017-06-06 | List App | Jquery File Type Validation | 1:00
2017-07-06 | List App | Changes In to Product Model
|  | A. Product Listing page | 1:00
|  | B. Add Product | 1:00
|  | C. Edit Product | 1:00
2017-08-06 | List App | Working on Product Module
|  | A. Working on Product Controller Changes in csv file upload code and sample file code and export code | 3:00
|  | B. Working on Jquery Validation on Product | 1:00
|  | C .Working on Data base in Prduct table | 1:00
|  | D. Changes On Add Product Form | 1:00
|  | E. Changes On Edit Product Form | 1:00
2017-09-06 | List App | Working on Supplier Module
|  | A. Working on Add Supplier Form with edit form and jquery validation | 2:00
|  | B. R&D for Boot strap Validation | 2:00
2017-12-06 | List App | Worknig on Client Change
|  | R&D for XLSX fle upload in Product module | 5:00
|  | changes some new fields in Product table | 0:30
|  | Working on Add product form | 1:00
|  | Edit product form | 1:00
|  | CSV upload type validation in Product name field | 1:00
13/6/2017 | List App | Working on Product listing page | 2:00
|  | Working on Genrate Sample File and Export XLSX file | 2:00
14/6/2017 | List App | Working on Company Module i.e add ,edit ,delete ,create a table | 1:00
|  | Create Pack size and packing type module | 3:00
15/6/2017 | List App | Fix Reported issues | 2
16/06/2017 | List App | Fix Mantis Issues | 2
Rahul Nakum
|  | Module | Hour | Comments
|  | Login | 2
|  | Forgot Password | 1
|  | Dashbord | 1
|  | Change Password | 1
|  | View / Edit Profile | 2
|  | Left Navigation | 1
|  | Add Product | 2 | add product with this fields- Product Name Company Packing Details MRP
|  | edit Product | 1
|  | View Product | 2
|  | Add Supplier | 2
|  | Edit Supplier | 2
|  | view Supplier | 2
|  | Delete Supplier | 1
|  | Add Product | 1 | Add Fields- Form,MRP,Rate,Packing Type, Pack Size, Schedule
|  | Edit Produuct | 1 | Add Fields- Form,MRP,Rate,Packing Type, Pack Size, Schedule
|  | Product View | 1 | Show New field
|  | Add / Edit Supplier | 3 | Add multiple Company And Contact Person with Contact Number at a time Add More (+/-) Button
|  | Company Add /edit/view /Delete | 2 | With validation
|  | Packin Type Add /edit/view /Delete | 2 | With validation
|  | Schedule Add /edit/view /Delete | 2 | With validation
|  | Product Add/Edit | 3 | Show Suggetion For Company Name, Form, Packing Type ,Pack Size ,Schedule
|  | Add / Edit Supplier | 2 | Change Company Deal multiple input box to Multiselect box with database compny and Change Validation for contact person ,mobile number
|  | Add /Edit supplier | 2 | Area Selection Auto suggestion
|  | fixed Reported Issue | 2 | Fix issue testing bug issue